## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Research AI response evaluation methods | Must Have | — | Vinod | Completed
Sprint 1 | Sprint 1 | US-02 | Design system architecture | Must Have | US-01 | Vinod | Completed
Sprint 1 | Sprint 1 | US-03 | Build evaluation input interface | Must Have | US-02 | Vinod | Completed
Sprint 1 | Sprint 1 | US-04 | Build reference knowledge base | Must Have | US-01,US-02 | Vinod | Completed
Sprint 1 | Sprint 1 | US-05 | Implement semantic evidence retrieval | Must Have | US-04 | Vinod | Completed
Sprint 1 | Sprint 1 | US-06 | Implement AI response validation | Must Have | US-05 | Vinod | Completed
Sprint 2 | Sprint 2 | US-07 | Implement evaluation agents | Should Have | US-06 | Vinod | Completed
Sprint 2 | Sprint 2 | US-08 | Build evaluation result dashboard | Should Have | US-06 | Vinod | Completed
Sprint 2 | Sprint 2 | US-09 | Perform system testing and validation | Must Have | US-06 | Vinod | Completed
Sprint 3 | Sprint 3 | US-10 | Implement Completeness Judge Agent | Must Have | US-07 | Vinod | Completed
Sprint 3 | Sprint 3 | US-11 | Implement Verdict Agent and weighted evaluation | Must Have | US-10 | Vinod | Completed
Sprint 3 | Sprint 3 | US-12 | Implement per-dimension scoring and results display | Must Have | US-11 | Vinod | Completed
Sprint 3 | Sprint 3 | US-13 | Implement batch evaluation module | Must Have | US-12 | Vinod | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | T01 | Research AI response evaluation methods | — | — | Vinod | Others | 3- Completed | 8 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T02 | Design system architecture | — | — | Vinod | Design | 3- Completed | 8 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T03 | Develop evaluation input interface | — | — | Vinod | Build | 3- Completed | 10 | 0 | 0 | 2 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T04 | Collect and prepare TruthfulQA and SQuAD datasets | — | — | Vinod | Others | 3- Completed | 8 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T05 | Implement text cleaning and standardization | — | — | Vinod | Others | 3- Completed | 8 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T06 | Implement document chunking | — | — | Vinod | Others | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T07 | Generate Sentence Transformer embeddings | — | — | Vinod | Build | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
US-04 | T08 | Build FAISS vector store and metadata | — | — | Vinod | Build | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
US-05 | T09 | Implement semantic evidence retrieval | — | — | Vinod | Build | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
US-06 | T10 | Implement response validation and scoring | — | — | Vinod | Build | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
US-06 | T11 | Integrate retrieval with validation service | — | — | Vinod | Integration Test | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2
US-06 | T12 | Test evaluation with and without reference answer | — | — | Vinod | System Test | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0
US-07 | T13 | Build Relevance Judge Agent | 2026-09-07 | 2026-09-08 | Vinod | Build | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T14 | Build Accuracy Judge Agent | 2026-09-09 | 2026-09-12 | Vinod | Build | 3- Completed | 5 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T15 | Build Hallucination Detection Agent | 2026-09-11 | 2026-09-13 | Vinod | Build | 3- Completed | 5 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T16 | Integrate agents with Evaluation Orchestrator | 2026-09-13 | 2026-09-14 | Vinod | Integration Test | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T17 | Test agent consistency using benchmark cases | 2026-09-14 | 2026-09-15 | Vinod | System Test | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
US-10 | T18 | Build Completeness Judge Agent | 2026-09-16 | 2026-09-17 | Vinod | Build | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T19 | Test complete and incomplete responses | 2026-09-17 | 2026-09-17 | Vinod | System Test | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T20 | Build Verdict Agent and weighted evaluation | 2026-09-18 | 2026-09-19 | Vinod | Build | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T21 | Test verdict thresholds and weighted scores | 2026-09-19 | 2026-09-19 | Vinod | System Test | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T22 | Integrate per-dimension scoring and results display | 2026-09-20 | 2026-09-21 | Vinod | Integration Test | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T23 | Test final score, dimension scores and verdict display | 2026-09-21 | 2026-09-21 | Vinod | System Test | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T24 | Build batch CSV evaluation module | 2026-09-22 | 2026-09-22 | Vinod | Build | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T25 | Add batch evaluation API endpoint | 2026-09-22 | 2026-09-22 | Vinod | Build | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T26 | Test 3-record and 5-record batch datasets | 2026-09-23 | 2026-09-23 | Vinod | System Test | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T27 | Run final 10-record batch validation | 2026-09-24 | 2026-09-24 | Vinod | System Test | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | None | Started research on AI response evaluation methods
Sprint 1 | Day 2 | None | Completed research and finalized evaluation approach
Sprint 1 | Day 3 | None | Designed system architecture and project modules
Sprint 1 | Day 4 | None | Developed evaluation input interface
Sprint 1 | Day 5 | Dataset preparation required | Prepared TruthfulQA and SQuAD reference data
Sprint 1 | Day 6 | None | Implemented data cleaning and chunking
Sprint 1 | Day 7 | None | Generated embeddings and prepared FAISS vector store
Sprint 1 | Day 8 | Retrieval integration required | Implemented semantic evidence retrieval
Sprint 1 | Day 9 | None | Integrated response validation and scoring
Sprint 1 | Day 10 | None | Tested evaluation with reference answer
Sprint 1 | Day 11 | Reference input handling issue | Updated system to support evaluation without reference answer
Sprint 1 | Day 12 | None | Tested evidence-based evaluation without reference answer
Sprint 1 | Day 13 | None | Reviewed Sprint 1 implementation and documentation
Sprint 1 | Day 14 | None | Completed Sprint 1 review and prepared remaining tasks
Sprint 2 | Day 1 | Understanding Milestone 2 requirements | Reviewed requirements and planned implementation
Sprint 2 | Day 2 | Agent implementation setup | Started Relevance Judge Agent
Sprint 2 | Day 3 | None | Implemented Relevance Agent logic
Sprint 2 | Day 4 | None | Tested relevance evaluation
Sprint 2 | Day 5 | None | Started Accuracy Judge Agent
Sprint 2 | Day 6 | None | Implemented Accuracy Agent logic
Sprint 2 | Day 7 | Import/integration issue | Fixed module and import issues
Sprint 2 | Day 8 | None | Started Hallucination Detection Agent
Sprint 2 | Day 9 | None | Implemented hallucination claim checking
Sprint 2 | Day 10 | None | Tested supported and unsupported claims
Sprint 2 | Day 11 | None | Integrated evaluation components
Sprint 2 | Day 12 | None | Tested complete evaluation flow
Sprint 2 | Day 13 | None | Fixed issues and performed final testing
Sprint 2 | Day 14 | None | Completed Milestone 2 and verified results
Sprint 3 | Day 1 | None | Reviewed Milestone 3 requirements and started Completeness Judge Agent
Sprint 3 | Day 2 | None | Implemented and tested Completeness Judge Agent
Sprint 3 | Day 3 | None | Tested complete and incomplete response coverage
Sprint 3 | Day 4 | None | Implemented Verdict Agent with weighted evaluation
Sprint 3 | Day 5 | Verdict threshold issue | Adjusted verdict logic for incomplete responses
Sprint 3 | Day 6 | None | Tested verdict thresholds and weighted scores
Sprint 3 | Day 7 | None | Integrated per-dimension scores and final results
Sprint 3 | Day 8 | None | Verified final score, dimension scores and verdict display
Sprint 3 | Day 9 | None | Implemented batch CSV evaluation service
Sprint 3 | Day 10 | None | Added batch evaluation API endpoint
Sprint 3 | Day 11 | None | Tested batch evaluation with 3-record and 5-record datasets
Sprint 3 | Day 12 | None | Ran final 10-record batch validation
Sprint 3 | Day 13 | None | All 10 batch records processed successfully with zero failures
Sprint 3 | Day 14 | None | Completed Milestone 3 and verified results

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 |  |  | Vinod | Maintain Agile documentation regularly | Make changes without testing | Continue modular development and testing | Update Agile records regularly and test each module after changes
2 | Sprint 2 | 2026-09-07 | 2026-09-15 | Vinod | Regularly test each agent during development | Making changes without testing | Modular development and step-by-step testing | Tested Relevance, Accuracy and Hallucination agents and integrated them with the orchestrator
3 | Sprint 3 | 2026-09-16 | 2026-09-24 | Vinod | Continue systematic testing of each milestone module | Changing evaluation logic without threshold testing | Modular implementation and test-driven validation | Completed Completeness, Verdict, scoring/results display and batch evaluation testing
4
5
6
7