## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Vinod |  | Validation submission was blocked when no reference answer or source document was provided | Sprint 1 | Vinod | Logical | Updated the validation flow to allow evidence-based evaluation without a reference answer |  | Closed | Fixed and tested successfully
2 | Vinod | 2026-09-19 | Incomplete responses were initially classified as CORRECT by the Verdict Agent | Sprint 3 | Vinod | Logical | Updated verdict logic so completeness score <= 3 produces PARTIALLY CORRECT | 2026-09-19 | Closed | Retested successfully

## Sheet2
Logical
User Interface
Maintainability
Standards
Others